## Detail1 (hidden)
Details for Summe von Planned Effort in h - Responsible: Tristan Buls, Planned for Sprint #: 0 (+)
# | Task | Result | Responsible | Support by | Planned for Sprint # | Planned Effort in h | Realized in Sprint # | Real Effort in h
98 | Best performing Pizza Franchise |  | Tristan Buls | Peter Hofmann | 4
86 | Added folder for exporting | have seperate codes for each individual boxes | Tristan Buls | Peter Hofmann | 3 | 2 | 3 | 2
84 |  | Added SQL-Query pizza ingredients | Tristan Buls | Peter Hofmann | 3 | 2 | 3 | 2
59 | creating diagramm ideas for franchise and store overview 1 | Register four new diagramm ideas with description and pictures into the word | Tristan Buls |  | 2 | 2 | 2 | 4
57 | Implemented the franchise overview data into the website | Backend for the the stat overview is now visible on the website | Tristan Buls | Peter Hofmann | 2 | 4 | 2 | 5
55 | creating diagramm ideas store overview | created fitting endpoints for each unexplored diagramm | Tristan Buls |  | 3 | 4
54 | Implement diagramm ideas store overview |  | Tristan Buls |  | 3 | 4
8 | Initialize dummy data | Insert dummy data for the diagrams of the prototype | Tristan Buls |  | 1 | 2 | 1 | 1
53 | Implement diagram ideas for frachnise |  | Tristan Buls |  | 3 | 4
52 | creating diagramm ideas for franchise | created fitting endpoints for each unexplored diagramm | Tristan Buls |  | 3 | 4
11 | Tests (postman) | Read the documentation and try out Postman to test the data and see how it fits to our project | Tristan Buls | Fatima Irhzal | 1 | 2 | 1 | 1
40 | implent previous diagramm ideas 2 | finished diagramms for the frontend | Tristan Buls |  | 3
13 | Revise Sprint Log | The sprint log has been improved accordingly | Tristan Buls |  | 1 | 1 | 1 | 1
39 | Create endpoints for franchise and store stats overview | Created five finished Endpoints | Tristan Buls | Peter Hofmann | 2 | 3 | 2 | 2.5
37 | total pizzas sold Endpoint | Endpoint for total sold pizza | Tristan Buls |  | 2 | 1 | 2 | 1
30 | Interactive chart | Deep knowledge of interactive charts | Tristan Buls |  | 2 | 2 | 2 | 2
29 | Develop a Drop down menu for filters | Working drop down menu and filter | Tristan Buls |  | 2 | 2 | 2 | 2

## Detail2 (hidden)
Details for Summe von Real Effort in h - Responsible: Tristan Buls, Planned for Sprint #: 0 (+)
# | Task | Result | Responsible | Support by | Planned for Sprint # | Planned Effort in h | Realized in Sprint # | Real Effort in h
98 | Best performing Pizza Franchise |  | Tristan Buls | Peter Hofmann | 4
86 | Added folder for exporting | have seperate codes for each individual boxes | Tristan Buls | Peter Hofmann | 3 | 2 | 3 | 2
84 |  | Added SQL-Query pizza ingredients | Tristan Buls | Peter Hofmann | 3 | 2 | 3 | 2
59 | creating diagramm ideas for franchise and store overview 1 | Register four new diagramm ideas with description and pictures into the word | Tristan Buls |  | 2 | 2 | 2 | 4
57 | Implemented the franchise overview data into the website | Backend for the the stat overview is now visible on the website | Tristan Buls | Peter Hofmann | 2 | 4 | 2 | 5
55 | creating diagramm ideas store overview | created fitting endpoints for each unexplored diagramm | Tristan Buls |  | 3 | 4
54 | Implement diagramm ideas store overview |  | Tristan Buls |  | 3 | 4
8 | Initialize dummy data | Insert dummy data for the diagrams of the prototype | Tristan Buls |  | 1 | 2 | 1 | 1
53 | Implement diagram ideas for frachnise |  | Tristan Buls |  | 3 | 4
52 | creating diagramm ideas for franchise | created fitting endpoints for each unexplored diagramm | Tristan Buls |  | 3 | 4
11 | Tests (postman) | Read the documentation and try out Postman to test the data and see how it fits to our project | Tristan Buls | Fatima Irhzal | 1 | 2 | 1 | 1
40 | implent previous diagramm ideas 2 | finished diagramms for the frontend | Tristan Buls |  | 3
13 | Revise Sprint Log | The sprint log has been improved accordingly | Tristan Buls |  | 1 | 1 | 1 | 1
39 | Create endpoints for franchise and store stats overview | Created five finished Endpoints | Tristan Buls | Peter Hofmann | 2 | 3 | 2 | 2.5
37 | total pizzas sold Endpoint | Endpoint for total sold pizza | Tristan Buls |  | 2 | 1 | 2 | 1
30 | Interactive chart | Deep knowledge of interactive charts | Tristan Buls |  | 2 | 2 | 2 | 2
29 | Develop a Drop down menu for filters | Working drop down menu and filter | Tristan Buls |  | 2 | 2 | 2 | 2

## Tasklog
Group: Group 4 |  |  |  |  | Last update: 15.07.2024
# | Task | Result | Responsible | Support by | Planned for Sprint # | Planned Effort in h | Realized in Sprint # | Real Effort in h
1 | Planning, initial design | The group meets to discuss the project and the procedure | Daniel Schor | Peter Hofmann, Yannis Koerner | 0 | 1 | 0 | 1
2 | Setup Node.js, Typescript, GitHub | Every group member is ready to work on the project and all systems are working | Daniel Schor |  | 0 | 1 | 0 | 1
3 | Setup PostgreSQL | One group member takes care of the PostgreSQL setup and explains it to the other group members | Yannis Körner |  | 0 | 1 | 0 | 2
4 | Meetings with mister Bremm |  | Everyone |  | 0 |  | 5 | 2.5
5 | Project Plan (Meetings, ) | A group member takes care of a platform for collaboration and exchange and controls the group member's tasks and their progress | Peter Hofmann |  | 1 | 2
6 | First Mock Ups | Prototype of website is designed | Fatima Irhzal |  | 1 | 2 | 1 | 2
7 | Prototype frontend with Echarts | A simple website, with with a Bar Chart and Radar chart | Peter Hofmann | Fatima Irhzal | 1 | 6 | 1 | 6
8 | Initialize dummy data | Insert dummy data for the diagrams of the prototype | Tristan Buls |  | 1 | 2 | 1 | 1
9 | Connecting Database to backend | The Node.Js Backend is connected to the Database and can send requests/receive data | Daniel Schor | Yannis Körner | 1 | 1 | 1 | 1
10 | First API endpoints | The first API Endpoints are ready (but not finished) to be used/tested | Daniel Schor | Peter Hofmann | 1 | 8 | 1 | 8
11 | Tests (postman) | Read the documentation and try out Postman to test the data and see how it fits to our project | Tristan Buls |  | 1 | 2 | 1 | 1
12 | Limit functionalities (not final) | Expected functionalities of the app are set | Fatima Irhzal | Daniel Schor, Peter Hofman, Yannis Koerner | 1 | 1 | 2 | 2
13 | Revise Sprint Log | The sprint log has been improved accordingly | Tristan Buls |  | 1 | 1 | 1 | 1
14 | Brainstorm meeting | Discuss about Sprint Log Nr.2 -> What we plan to do during the sprint and what our goals are at the end from the sprint. | Everyone |  | 1 | 2 | 1 | 3
15 | Detailed Mockups | Detailed website design is finished | Fatima Irhzal |  | 1 | 1 | 2 | 3
16 | Import Pizza data to database | A group member takes care of importing the data into the database | Yannis Körner |  | 1 | 6 | 1 | 6
17 | Analyze needed Data | Data needed for frontend is located and analyzed | Yannis Körner | Daniel Schor | 1 | 4 | 2 | 6
18 | Adapt website layout to mockup | The website looks the same or similar to the mockup | Fatima Irhzal | Peter Hofmann | 2 | 8 | 2 | 8
19 | Build part of needed SQL queries 2 | SQL queries needed for data visualization are ready to be built into the backend | Daniel Schor |  | 2 | 5 | 2 | 5
20 | Develop Client quality logic | Logic, Endpoint and SQL-query for the customer quality score (of a store) is set | Daniel Schor |  | 2 | 4 | 2 | 5
21 | Revise Mockups | Issues with detailed Mockups are fixed | Everyone |  | 2 | 2 | 2 | 2
22 | Add Quality chart to website | The website now contains the Qualtiy diagram from the mockup | Peter Hofmann | Fatima Irhzal | 2 | 4 | 2 | 4
23 | Add Overview to Website |  | Peter Hofmann | Fatima Irhzal | 2 | 4 | 2 | 2
24 | Develop a Drop down menu for filters | Working drop down menu and filter | Tristan Buls |  | 2 | 2 | 2 | 2
25 | Interactive chart | Deep knowledge of interactive charts | Tristan Buls |  | 2 | 2 | 2 | 2
26 | Build Endpoints | New endpoints containing SQL-queires from the json file are set | Daniel Schor |  | 2 | 3 | 2 | 4
27 | connect the data from the endpoints to the test charts | The charts now show the real data, not dummy data ( Quality, monthlyRevenue B&W 5) | Peter Hofmann | Daniel Schor | 2 | 6 | 2 | 6
28 | Update revenue endpoint logic | The Revenue API-Endpoint has more query options and returns better structured data | Daniel Schor |  | 2 | 3 | 2 | 8
29 | top 5 chart visualization |  | Peter Hofmann | Daniel Schor | 2 | 3 | 2 | 3
30 | total pizzas sold Endpoint | Endpoint for total sold pizza | Tristan Buls | Daniel Schor | 2 | 1 | 2 | 1
31 | Implement Yearly, Quarterly, Montly Button | Buttons to change the timescale are implemented | Peter Hofmann |  | 2 | 1 | 2 | 1
32 | Create endpoints for franchise and store stats overview | Created five finished Endpoints(General stats) | Tristan Buls | Peter Hofmann | 2 | 3 | 2 | 3
33 | Implemented the franchise overview data into the website | Backend for the the stat overview is now visible on the website | Tristan Buls | Peter Hofmann | 2 | 4 | 2 | 5
34 | Implement Button funcunaltiy with charts (store) | The time buttons now affect the charts custom store page | Peter Hofmann | Daniel Schor | 2 | 3 | 2 | 5
35 | creating diagramm ideas for franchise and store overview 1 | Register four new diagramm ideas with description and pictures into the word | Tristan Buls |  | 2 | 2 | 2 | 4
36 | Sprint 3 planning meeting |  | Everyone |  | 2 | 2 | 2 | 2
37 | Implement Individual StoreOverview (Total Revenue,Total Pizzas,Total Orders,Average Order Value) including endpoint | the StoreOverview no works with storeid and date | Peter Hofmann | Tristan Buls | 2 | 1 | 2 | 3
38 | Implement Button funcunaltiy with charts (Business) | The time buttons now affect the charts on the main brand page | Peter Hofmann |  | 2 | 1 | 2 | 3
39 | Restructure Porject | The Project has a consistent, logical and easy to use structure and Typescript is being used in both front- and backend. | Daniel Schor |  | 2 | 4 | 2 | 10.5
40 | Build part of needed SQL queries 1 | SQL queries needed for data visualization are ready to be built into the backend | Yannis Körner | Daniel Schor | 2 | 7 | 2 | 5
41 | Add SQL queries to queries json file | The queries json file now contains more SQL queries | Yannis Körner | Daniel Schor | 2 | 1 | 2 | 2
42 | Creating er diagram and relational table schema | Detailed er diagram and relational table schema | Yannis Körner |  | 2 | 1 | 2 | 1
43 | Endpoint Total Revenue all stores by date | Endpoint for total revenue for all stores | Yannis Körner |  | 2 | 1 | 2 | 1
44 | Add Revenue Bar Chart | The Franchise view contains a bar chart with the total revenues of the stores in the selected timeframe. | Daniel Schor | Peter Hofmann | 3 | 3 | 2 | 4
45 | Finish Revenue line Chart | The revenue line chart is now dynamic. | Daniel Schor | Peter Hofmann | 3 | 2 | 2 | 2
46 | Add Revenue line Chart Filter Options | The line chart has now filter options for stores with best sustainable growth and the opposite. | Daniel Schor |  | 3 | 3 | 2 | 3
47 | Add Bar Chart as Filter and as a Store select option | The Bars on the Barchart are clickable. If clicked the Store view of the relative bar is opend. The names of the bars are the checkboxes for the revenue Line Chart. | Daniel Schor |  | 3 | 8 | 2 | 9
48 | Implement Custom Button | Buttons to change the timescale to a custom date are implemented | Peter Hofmann |  | 3 | 1 | 2 | 1
49 | Endpoint Add Revenue Bar chart | The query selects the purchase date and sums the total revenue for each day. | Yannis Körner |  | 3 | 1 | 3 | 1
50 | New diagramm ideas for placeholder | Added new diagramm ideas for both views | Tristan Buls |  | 3 | 2 | 3 | 1
51 | Write HTML script | Build html document to later on add charts etc. | Fatima Irhzal |  | 3 | 3 | 3 | 3
52 | Layout & Typography | Create a fitting layout with different containers fonts and styles. | Fatima Irhzal |  | 3 | 2 | 3 | 8
53 | Create Box for each chart | Creating boxes in CSS to seperate the charts | Fatima Irhzal |  | 3 | 2 | 3 | 4
54 | Name charts and add titles | Using HTML to allow users to understand dashboard content | Fatima Irhzal |  | 3 | 2 | 3 | 1
55 | Frontend Development | Using HTML for content structuring and CSS for layout and visual presentation of dashboard for franchise & store view | Fatima Irhzal |  | 3 | 8 | 3 | 4
56 | Adapt and add scripts to HTML | to display charts | Fatima Irhzal |  | 3 | 1 | 4 | 4
57 | creating diagramm ideas for franchise | Adjusted and added new diagramms suggestions in the word file for the franchise overview | Tristan Buls |  | 3 | 4 | 3 | 3
58 | Implement diagramm ideas store overview | Implement Pizza Ingredient diagramm in the store overview | Tristan Buls | Peter Hofmann | 3 | 5 | 3 | 4
59 | creating diagramm ideas store overview | Adjusted and added new diagramms suggestions in the word file for the store overview | Tristan Buls |  | 3 | 4 | 3 | 4
60 | Endpoint relationship between price and popularity of the pizzas | Endpoint for showing the relationship between price and popularity of the pizzas | Yannis Körner |  | 3 | 2 | 3 | 2
61 | Add time filter for the franchise/store | Add time filter to all the numbers and charts by clicking a filter at the top of the view. | Fatima Irhzal |  | 3 | 2 |  | 2
62 | Endpoint region-total-product | Endpoint and implemantion in the map for showing the top product per store in the map | Yannis Körner |  | 3 | 2 | 3 | 1
63 | Endpoint ABC analysis Pizza Products | Endpoint and Chart for identifying pizza products in abc scheme | Yannis Körner |  | 3 | 3 | 3 | 3
64 | Endpoint ABC analysis Costumer | Endpoint and Chart for identifying costumers in abc scheme | Yannis Körner |  | 3 | 3 | 3 | 3
65 | Endpoint Customer-Lifetime-Value | Endpoint calculates the customer lifetime value by providing data on average spending per purchase, total purchases, and total spending for each customer - obselot now abc scheme | Yannis Körner |  | 3 | 1 | 3 | 1
66 | creating navigation menu | a sidebar was implemented which allows for navigation between differernt stores | Peter Hofmann |  | 3 | 4 | 3 | 3
67 | implement chart to show connection between pizzas(Heatmap) | the chart shows pizza pairs (What is ordered together) | Peter Hofmann |  | 3 | 1 | 3 | 3
68 | Help Peter implementig the Heatmap | Heatmap displays correct pizza pairs | Daniel Schor |  | 3 | 1 | 3 | 2
69 | implement map on company site | the Map now is visible on the main companysite not on a whole different site | Peter Hofmann | Daniel Schor | 3 | 3 | 3 | 3
70 | % of sales by Pizza size (including endpoint) | % of sales by Pizza size for company and Individual store (Pie Chart) | Peter Hofmann |  | 3 | 3 | 3 | 3
71 | Endpoint Customer-Segmentation-Analysis | Endpoint retrieves data, including average spending per purchase, total purchases, customer lifetime, and geographical coordinates ->obselot now abc scheme | Yannis Körner |  | 3 | 1 | 3 | 1
72 | export buttons in Ui file | the buttons now a not longer in HTML but in a ui.ts file(custom button fixed maybe) | Peter Hofmann |  | 3 | 2 | 3 | 2
73 | Edit PizzaPair Endpoint | the EndPoint now can take in date and StoreID as value | Peter Hofmann | Tristan Buls | 3 | 0.5 | 3 | 2
74 | Loading animation for charts | Shows a animation when data for the chart is loading | Peter Hofmann |  | 3 | 2 | 3 | 1
75 | Remove js code from HTML files | the html now no longer contains code (the js is reduced to the possible minimum) as of 12.06 | Peter Hofmann | Tristan Buls | 3 | 2 | 3 | 2
76 | Create SQL-Query for Pizza Ingredients | Added SQL-Query pizza ingredients | Tristan Buls | Peter Hofmann | 3 | 2 | 3 | 2
77 | remove duplication General Statistics | the General Statistics is now no longer in 2 files but in one and can switch cases between francise and company | Peter Hofmann | Tristan Buls | 3 | 2 | 3 | 2
78 | Adjusted the code for general statistics | have seperate codes for each individual boxes | Tristan Buls | Peter Hofmann | 3 | 2 | 3 | 2
79 | Sprint 4 planning meeting |  | Everyone |  | 3 | 3 | 3 | 3
80 | Adapt graph size to box size | Graph needs to fill box-width. Problem: When trying to regulate sizing, graph width split in half | Fatima Irhzal |  | 3 | 1 | 3 | 4
81 | fix timeButton Functionality after export to ButtonUI | TimeButtons now work on both sides | Peter Hofmann |  | 3 | 1 | 3 | 1
82 | Bug: Committment issue | Comitting was not possible. Synchronization of path took two days. Deleted and cloned from 0. Restarted frontend coding. | Fatima Irhzal |  | 3 | 0 | 3 | 6
83 | Chart relationship between price and popularity of the pizzas | Chart for showing the relationship between price and popularity of the pizzas | Yannis Körner |  | 4 | 3 | 4 | 3
84 | Chart ABC analysis Pizza Products | Chart for identifying pizza products in abc scheme | Yannis Körner |  | 4 | 3 | 4 | 4
85 | Chart ABC analysis Costumer | Chart for identifying costumers in abc scheme | Yannis Körner |  | 4 | 3 | 4 | 4
86 | Fix some things Endpoint ABC Anaylsis | Fixing some things in the ABC Analysis Customer and Pizza to adapt to the chart | Yannis Körner |  | 4 | 1 | 4 | 1
87 | Create Website Design | A design of how the finished website should be structured. This is a help for organisation/planning. Each part of this design has names of the responsible person attached to it. | Daniel Schor |  | 4 | 3 | 4 | 8
88 | Fix StoreID Bug Mainpage |  | Peter Hofmann | Daniel Schor | 4 | 2 |  | 2
89 | Fix Sidebar overlapping | Sidebar can now be clicked even if over charts | Peter Hofmann |  | 4 | 2 | 4 | 2
90 | Implement Sidebar on Franchise view | Sidebar now available on franchise view | Peter Hofmann |  | 4 | 1 | 4 | 2
91 | Create Description for charts | the user now can easily see what the chart shows | Peter Hofmann | Fatima Irhzal | 4 | 1 | 4 | 1
92 | Implement profit/revenue for pizza size diagramm (edit endpoint aswell) | When hovered u now can see how much was earned | Peter Hofmann |  | 4 | 3 | 4 | 3
93 | Franchise view resize(charts) | Using html to resize dashboard sections | Fatima Irhzal |  | 4 | 2 | 4 | 1
94 | Ui Resize | the buttons and sidebar are now a better size | Peter Hofmann |  | 4 | 3 | 4 | 2
95 | Fix custom date Button on mainpage | the custom button now no longer reloads the site | Peter Hofmann |  | 4 | 1 | 4 | 2
96 | Group stores by location in Sidebar | The stores now are in a group instead of under each other | Peter Hofmann | Fatima Irhzal | 4 | 3 | 4 | 4
97 | info about chart on hover | if you hover over the name of the chart the content of the chart is now being explained | Peter Hofmann | Tristan Buls | 4 | 3 | 4 | 4
98 | Best performing Pizza Franchise |  | Tristan Buls | Peter Hofmann | 4 | 1 | 4 | 1
99 | Build sections for different categorys | Building differnt sections to have a clear overview. Rearrange boxes if needed. | Fatima Irhzal |  | 4 | 5 | 4 | 3
100 | New idea for franchise view diagram | Finished diagram idea | Tristan Buls |  | 4 | 2 | 4 | 1
101 | Make SQL endpoint | Finished SQL endpoint | Tristan Buls |  | 4 | 2 | 4 | 2
102 | Backend for diagram for franchise view | Finished the backend from the diagramm | Tristan Buls |  | 4 | 2 | 4 | 2
103 | Add map to sidebar like the mockup(old, will not be used) | a small map is now visible at the bottom of the sidebar | Peter Hofmann |  | 4 | 1 |  | 1
104 | Adjusted pizzaingredient endpoint and diagramm | Refactor pizzaIngredients function for better performance and readability | Tristan Buls |  | 4 | 3 | 4 | 3
105 | Seperate general statistic function | Have a seperate funtion for every API access | Tristan Buls |  | 4 | 1 | 4 | 1
106 | Fix selection of pizza ingredients by default | Update pizzaIngredients chart with selected series deselected by default | Tristan Buls |  | 4 | 1 | 4 | 1.5
107 | Create dummy ABC Chart | Created a dummy ABC Chart | Yannis Körner |  | 4 | 1 | 4 | 1
108 | Implement forecast graphs | Java-Script coding, style and display definition in html and css. | Tristan Buls |  | 4 | 6 | 5 | 5
109 | Sprint 5 planning meeting |  | Everyone |  | 4 | 2 | 4 | 2
110 | Adjusted pizzaingredient diagramm to mockup | Pizzaingredient diagram looks more like the mock up and has a fitting title | Tristan Buls |  | 4 | 1 | 4 | 1
111 | create endpoint and chart overview documentation | writing for the documentation and presentation a overview about the charts and endpoints | Yannis Körner | Daniel Schor | 5 | 8 | 5 | 8
112 | Presentation slides | Create draft and start presentation | Everyone |  | 5 | 2
113 | Custom Date position and remove data input field until pressed | the Button is now in the right position, and the input field is only shown when clicked | Peter Hofmann |  | 5 | 1 | 5 | 2
114 | Implement Active Buttons | if a button is clicked the color changes | Peter Hofmann |  | 5 | 1 | 5 | 1
115 | update the readme.md file | update the readme.md file. Include a tutorial dateiled tutorial to install. | Yannis Körner |  | 5 | 1 | 5 | 1
116 | clean the code | clean the code. Delete unused code… | Yannis Körner | Daniel Schor | 5 | 4 | 5 | 4
117 | final revision task log | revison of the task log | Yannis Körner |  | 5 | 1 | 5 | 1
118 | randomColor function replace with color pallete | https://echarts.apache.org/en/theme-builder.html | Peter Hofmann |  | 5 | 2 |  | 2
119 | Popular Pizzas overtime for mainpage and Franchise | One of the PlaceHolders now contains a chart which shows the popularity of all Pizzas | Peter Hofmann |  | 5 | 4 | 5 | 5
120 | Name new charts + define design | New charts will be named and the style will be defined | Fatima Irhzal |  | 5 | 2 | 5 | 2
121 | Add icons | Add icons to improve design | Fatima Irhzal |  | 5 | 1 | 5 | 1
122 | Fork project (New Frontend attempt) | New branch of project exists with better code quality in the frontend. | Daniel Schor |  | 5 | 1 | 4 | 1
123 | NewTopbar & Sidebar | Top- and Sidebar are redone in new branch. | Daniel Schor |  | 5 | 2 | 4 | 2
124 | html layout franchise view | create new html script | Daniel Schor |  | 5 | 3 | 5 | 2
125 | html layout store view | create new html script | Daniel Schor |  | 5 | 6 | 5 | 1
126 | Comparison of stats overview | Having the comparison from the stats showed before to the current stats | Tristan Buls |  | 5 | 1 | 5 | 1
127 | Adjust Pizza Ingredients chart to Mock Up View | Having the view for the current timeframe and remove the activate funtion | Tristan Buls |  | 5 | 2
128 | Add forecast stats | Having stats that show information to the general stats from the forecast diagrams | Tristan Buls |  | 5 | 3
129 | Bugfixes & Optimizations | Various remaining bugs are fixed and performance issues detected and improved. | Daniel Schor |  | 5 | 3 | 5 | 8
130 | Fine tuning of all data |  | Everyone |  | 5 | 2
131 | Fix Timebutton in the end | Time buttons again stopped working, will be fixed at the end | Peter Hofmann | Daniel Schor | 5 | 2 | 5 | 3
132 | abc legend | overhaul of the abc legend and added text and clarify the chart | Yannis Körner |  | 5 | 1 | 5 | 1
133 | Documentation front end Usecase of the Charts | Documentation about the frontend and its capabilities, screenshots for later use in Presentation | Peter Hofmann |  | 5 | 3 |  | 1
134 | connect html diagrams and data | connect html diagrams and data in new branch | Fatima Irhzal |  | 5 | 3 | 5 | 8
135 | Style | new css files for design | Daniel Schor | Fatima Irhzal | 5 | 8 | 5 | 5
136 | Fix tooltip forecast orders | Show everything correctly in the tooltip forecast orders box | Tristan Buls |  | 5 | 1 |  | 1
137 | Import Sidebar and timebuttons in new branch | the sidebar and timebuttons now work in the new branch | Peter Hofmann |  | 5 | 1 | 5 | 3
138 | abc pizza different size | you can filter the different sizes in the abc chart for pizza | Yannis Körner |  | 5 | 1 | 5 | 1
139 | abc customer search | Chart ABC Anaylsis Customer you can search customerID | Yannis Körner |  | 5 | 2 | 5 | 2
140 | improving code in css | improving the container in css | Yannis Körner |  | 5 | 2 | 5 | 2
141 | merging abc and pizza popularity | merged the charts abc pizza and customer and Relationship between price and popularity of pizzas from experimental to main | Yannis Körner |  | 5 | 3 | 5 | 3
142 | abc pizza chart change view | changed the view to descinding total orders | Yannis Körner |  | 5 | 1 | 5 | 1
143 | Fix tooltip for the headlines | tooltip now is displayed | Peter Hofmann |  | 5 | 1 | 5 | 3
144 | abc customer chart change view | changed the view to descinding total orders | Yannis Körner |  | 5 | 1 | 5 | 1
145 | abc new tooltips | added total order and average order value for each customer | Yannis Körner |  | 5 | 2 | 5 | 2
146 | revenue forecast diagram | defined new diagram for franchise view; bug: server not found & diagram not shown | Fatima Irhzal |  | 5 | 3 | 5 | 10
147 | loading display | new loading animation for diagrams | Daniel Schor | Fatima Irhzal | 5 | 2 | 5 | 2
148 | fixing PizzaPopularity | The chart now shows more then a month, and if the timespan is to big only shows weekly informations | Peter Hofmann |  | 5 | 1 | 5 | 2
149 | bug fixing ui | fixing bugs in the ui and storecharts code | Yannis Körner |  | 5 | 3 | 5 | 3
150 | Implement duration and timespan buttons | the bottoms on the top now adept to the date and show duration | Peter Hofmann |  | 5 | 1 | 5 | 1
151 | Adjust Pizzasize chart to be better readable | the user now can read the different categorises | Peter Hofmann |  | 5 | 1 | 5 | 1
152 | implement averageOrderFrequency | added average vor customer statistics | Fatima Irhzal |  | 5 | 3 | 5 | 6
153 | css tooltips visible parrent container | allow the tooltip of the charts to show in the parrent container | Yannis Körner |  | 5 | 1 | 5 | 1
154 | update average order frequency | change api endpoint | Peter Hofmann |  | 5 | 1 | 5 | 1
155 | finalize code abc and relationship pizza | finalize the code for the submission | Yannis Körner |  | 5 | 2 | 5 | 2
156 | trying to implement abc tooltip pizza amount | tryring to implement abc tooltip for showing the sold amount of pizza for each customer | Yannis Körner |  | 5 | 3 | 5 | 3
157 | Add percentage increase info for Stats | Stats now have percentage increase info. The percentage increase is taken from the same time duration as the period to date. | Daniel Schor |  | 5 | 1 | 5 | 1
158 | Adjust diagram sizes and names | Diagrams now fit better on the website and have more descriptive names. | Daniel Schor |  | 5 | 2 | 5 | 2
159 | Project management | Manage project team to ensure successful project closure. | Daniel Schor |  | 5 | 2 | 5 | 2
160 | Implement fitting icons | Find and implement fitting icons for better illustration of functionality. | Daniel Schor |  | 5 | 2 | 5 | 2
161 | Add toggle functionality for bar chart | Bar chart can now be toggled to be two sided. | Daniel Schor |  | 5 | 2 | 5 | 2
162 | Presentation design | choosing the presantion design | Yannis Körner |  | 5 | 1 | 5 | 1
163 | presentation draft | creating the draft for the presentantion | Yannis Körner | Fatima Irhzal | 5 | 4 | 5 | 4
164 | presentation finalize | finalize the presentation | Yannis Körner |  | 5 | 4 | 5 | 4
165 | presentation draft (2) | creating the draft for the presentantion (insights,frameworks&technologies) | Fatima Irhzal | Yannis Körner | 5 | 1 | 5 | 1
| Fix tooltips and namings | The charts and other objects are better titled and have better description. | Daniel Schor |  | 5 | 1 | 5 | 1
| Meeting | Meeting to fix last bugs | Everyone |  | 5 | 2 | 5 | 5
168 | Word with functions | Explanation for the use of diagramms | Tristan Buls |  | 5 | 2 | 5 | 2
169 | Adjusting endpoints for franchise and shop overview | New endpoints for overall stats for store and franchise view | Tristan Buls |  | 5 | 5 | 5 | 7
170 | Endpoints for forecast | New Endpoints for store view forecast | Tristan Buls |  | 5 | 2 | 5 | 4
171 | Building new Queries for franchise, store and forecast view | New queries for the endpoints | Tristan Buls |  | 5 | 4 | 5 | 4
172 | Endpoints for orders per hours graph | Endpoints for ready to be used for the diagramm | Tristan Buls |  | 5 | 1 | 5 | 1
173 | Building the orders per hour diagramm | Finished orders per hours diagramm | Tristan Buls |  | 5 | 3 | 5 | 5
174 | Fix last minute bugs | Small bugs and unfinished tasks are now done | Peter Hofmann | Daniel Schor | 5 | 2 | 5 | 3
175 | Integrate all my graphs and stats into the HTML a | Put the stats instead of the placeholders and puting in graphs | Tristan Buls |  | 5 | 3 | 5 | 3
176 | Adjusting and fixing diagramms and stats | Adjusted everything to the current version from our project | Tristan Buls |  | 5 | 5 | 5 | 5
[6 empty] | 427.5 |  | 491.5
Only one name per line
float between 1 and 8
float between 1 and 8
Reasonable & descriptive name
An evaluation, whether the result was met successfully, should be possible
Multiple names but as few as possible
Sprint 1 summary/goals
- database set
- backend ready
- design and functionality of app planned
Sprint 2 goals
- finished design
- set functionality
- working charts
- prototype website
Sprint 3 goals
- most functionality ready
- design as in mockups
- fixing issues and refining
Sprint 4 goals
- finished website
- documentation
- presentation

## Param (hidden)
Sprint # | Status | Risk Status
1 | Initial | Open
2 | Started | Issue
3 | Cancelled | Closed
4 | Done

## Tabelle1
Planned for Sprint # | (Alle)
Responsible | Summe von Planned Effort in h | Summe von Real Effort in h
Daniel Schor | 85 | 102.5
Everyone | 17 | 19.5
Fatima Irhzal | 53 | 83
Peter Hofmann | 92.5 | 106
Tristan Buls | 89 | 86.5
Yannis Körner | 90 | 93
(Leer)
Gesamtergebnis | 426.5 | 490.5